## R1
PCM | Region | Count sites | Hub Site | Fault Level | PCM Created At | Elapsed Duration(Hrs) | Creat Fault First Time Occured | Power Source | Battery Backup Status | EM Field Feedback | Site Owner
PCM-20250105-00002270 | R1 | 1 | JBL2138 | Major | 2025-01-05 22:45:44 | 3943:06:11 | 2025-01-05 22:38:30 | Generator-SG | Dead | as per RC Director of Investors Authority feedback the Facilities Management refused to open the gate, we already requested official letter and support to open the gate, but still no response, Saudi responsible follow up with them to get officially feedback. | Latis
PCM-20250615-00001997 | R1 | 1 | QYM0888 | Major | 2025-06-15 19:13:06 | 82:38:49 | 2025-06-15 19:13:06 | SCECO | Vandalized | ETA 60 mins | Latis
| R4 | 1 | JED0925 | Critical | 2025-06-14 20:13:06 | 105:38:49 |  | Generator-SG | In progress | team on the way | Latis
| R5 |  | USMD0705 | Critical |  |  |  | SCECO | Weak | team on the way | Latis
| R4 |  | JED0123 |  |  |  |  | SCECO | In progress |  | Latis

## R2
PCM | Region | Count sites | Hub Site | Fault Level | PCM Created At | Elapsed Duration(Hrs) | Creat Fault First Time Occured | Power Source | Battery Backup Status | EM Field Feedback | Site Owner
PCM-20250421-00001074 | R2 | 1 | RIY2486 | Critical | 2024-01-31 01:22:03 | 12124:29:52 | 2024-01-31 01:13:03 | Generator-SG | Dead | site located in VIP Area and Generator switched off as per security request. | Latis
PCM-20250203-00001501 | R2 | 1 | RIY2719 | Critical | 2025-02-03 15:38:34 | 3254:13:21 | 2025-02-03 15:30:04 | Generator-SG | Vandalized | Access Issue As Site located inside Wonder Garden. | Latis
PCM-20250529-00002138 | R2 | 1 | RIY2903 | Major | 2025-05-29 17:27:00 | 492:24:55 | 2025-05-14 13:02:01 | SCECO | No BB | We face access Issue Due Boulevard Gate , STC Owner , access PG | Latis
| R4 |  | JED0190 |  |  |  |  | SCECO | Good |  | Latis

## R3
PCM | Region | Count sites | Hub Site | Fault Level | PCM Created At | Elapsed Duration(Hrs) | Creat Fault First Time Occured | Power Source | Battery Backup Status | EM Field Feedback | Site Owner
| R3 |  | HAL0947 |  |  |  |  | SCECO | Weak+Good |  | Zain

## R4
PCM | Region | Count sites | Hub Site | Fault Level | PCM Created At | Elapsed Duration(Hrs) | Creat Fault First Time Occured | Power Source | Battery Backup Status | EM Field Feedback | Site Owner
PCM-20250215-00000830 | R4 | 1 | MKJD0649 | Major | 2025-02-15 11:32:14 | 2970:19:41 | 2025-02-15 11:23:40 | SCECO | Dead | site located in aramco area access issue need special permission | Latis
PCM-20250611-00000037 | R4 | 1 | JED2394 | Critical | 2025-06-11 00:19:59 | 197:31:56 | 2025-06-10 22:04:05 | Generator-SG | Dead | Site access issue located in formula one /Site under relocation | Latis
NO PCM | R4 | 3 | TAF0156 | Critical | 2025-06-15 16:07:34 | 85:44:21 | In progress | Access issue, located on commercial building, due to pending rent billing | Latis
NO PCM | R4 | 2 | JED0674 | Major | 2025-06-15 18:30:01 | 83:21:54 | Dead | 25 m | Latis

## R5
PCM | Region | Count sites | Hub Site | Fault Level | PCM Created At | Elapsed Duration(Hrs) | Creat Fault First Time Occured | Power Source | Battery Backup Status | EM Field Feedback | Site Owner
PCM-20250531-00001907 | R5 | 1 | MAK0605 | Major | 2025-05-31 17:33:15 | 444:19:08 | 2025-05-30 17:59:05 | SCECO | Dead | Sectors are down due to TE issue and they are facing access issue. Access applied and waiting approval from court. | Latis
| R5 |  | MAK0605 |  |  |  |  | SCECO | Dead |  | Latis

## R6
PCM | Region | Count sites | Hub Site | Fault Level | PCM Created At | Elapsed Duration(Hrs) | Creat Fault First Time Occured | Power Source | Battery Backup Status | EM Field Feedback | Site Owner
PCM-20250615-00001771 | R6 | 1 | ABBS0151 | Major | 2025-06-15 17:00:57 | 84:50:58 | 2025-06-15 17:18:01 | Generator-SG | Dead | "Cluster owner team busy at BAH0173Other Mc team dispatched remanning ETA 30 m" | Latis